Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 05 February 2026 |
| --- | --- |
| Team ID | LTVIP2026TMIDS60803 |
| Project Name | Optimizing User, Group & Role Management with Access Control and Workflows |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | User Management | USN-1 | As an Admin, I can create new users in the system | 3 | High | Team |
| Sprint-1 | User Management | USN-2 | As an Admin, I can assign roles to users | 3 | High | Team |
| Sprint-1 | Group Management | USN-3 | As an Admin, I can create user groups | 2 | Medium | Team |
| Sprint-1 | Access Control | USN-4 | As an Admin, I can configure ACL for role-based access | 5 | High | Team |
| Sprint-1 | Authentication | USN-5 | As a user, I can log in securely using credentials | 2 | High | Team |
| Sprint-1 | Dashboard | USN-6 | As a user, I can view dashboard based on role | 5 | Medium | Team |

Total Story Points – Sprint 1 = 20

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-2 | Task Management | USN-7 | As a Project Manager, I can create tasks | 3 | High | Team |
| Sprint-2 | Task Management | USN-8 | As a Project Manager, I can assign tasks to team members | 3 | High | Team |
| Sprint-2 | Workflow Automation | USN-9 | As a system, task status changes follow workflow | 5 | High | Team |
| Sprint-2 | Approval Process | USN-10 | As a Manager, I can approve or reject tasks | 5 | Medium | Team |
| Sprint-2 | Notifications | USN-11 | As a user, I receive email notifications on updates | 2 | Medium | Team |
| Sprint-2 | Audit | USN-12 | As an Admin, I can track audit logs | 2 | Low | Team |

Total Story Points – Sprint 2 = 20

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-3 | Reporting | USN-13 | As an Admin, I can generate system reports | 5 | High | Team |
| Sprint-3 | Performance | USN-14 | As a user, system loads efficiently | 5 | Medium | Team |
| Sprint-3 | Security | USN-15 | As Admin, I can enforce password policies | 5 | High | Team |
| Sprint-3 | UI Enhancement | USN-16 | As user, I can experience improved UI | 5 | Low | Team |

Total Story Points – Sprint 3 = 20

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-4 | Integration | USN-17 | As Admin, I can integrate system with other modules | 5 | Medium | Team |
| Sprint-4 | Data Backup | USN-18 | As Admin, system data is backed up securely | 5 | High | Team |
| Sprint-4 | Monitoring | USN-19 | As Admin, I can monitor system usage | 5 | Medium | Team |
| Sprint-4 | Final Testing | USN-20 | As Team, we perform system testing & bug fixing | 5 | High | Team |

Total Story Points – Sprint 4 = 20

# Project Tracker (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 4 Days | 05 Feb 2026 | 08 Feb 2026 | 20 | 08 Feb 2026 |
| Sprint-2 | 20 | 4 Days | 09 Feb 2026 | 12 Feb 2026 | 20 | 12 Feb 2026 |
| Sprint-3 | 20 | 3 Days | 13 Feb 2026 | 15 Feb 2026 | 20 | 15 Feb 2026 |
| Sprint-4 | 20 | 3 Days | 16 Feb 2026 | 18 Feb 2026 | 20 | 18 Feb 2026 |

# Velocity Calculation

Total Story Points = 80
Total Working Days = 14 Days

Average Velocity per Day:

80 ÷ 14 = 5.7 ≈ 6 Story Points per Day

# Burndown Chart Explanation (For Writing Section)

A Burndown Chart is a graphical representation of the work remaining versus time in a sprint. It is commonly used in Agile and Scrum methodologies to track project progress and ensure timely completion of tasks.

### Key Components:

- X-axis → Represents Sprint Days (Time)

- Y-axis → Represents Remaining Story Points (Work Left)

The chart shows how quickly the team is completing the assigned work during the sprint.

## 📊 Example: Sprint-1 (20 Story Points, 6 Days)

| Day | Remaining Story Points |
| --- | --- |
| Day 1 | 20 |
| Day 2 | 17 |
| Day 3 | 14 |
| Day 4 | 10 |
| Day 5 | 5 |
| Day 6 | 0 |

The chart gradually declines to zero, showing work completion over time.

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/

https://www.atlassian.com/agile/tutorials/burndown-charts

Reference:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts